| Report from D Lias re TMX WP Lessons Learned |  |
| --- | --- |
| Committee | Full Council |
| Committee date | 15 March 2021 |
| Report date | 15 March 2021 |

6.1

13.11

What went wrong: - Too little knowledge of the WBC Asset Register (only Shinfield entry was Legion building) and the Community Right to Bid (CRtB) scheme. - Too little knowledge of the asset e.g. 2nd ownership interest - No procedure existing for asset purchase - Estate agent (Christie’s) took SPC interest to relight interest in the property – not considered by WP as asset had been on the market for 3 years. - WP did not set achievable targets with timelines – too little information. - Potentially counterproductive outcome – if developer buys. What went well: - Full Survey (compromised by Covid and resident’s health) – identified c.£250k repairs and remedial work - AOC provided a report on potential for the asset – useful but abortive spend - Potential for developers to drop out if ERZ effect on residential development is sustained?. What could be improved: - Need procedure for steps towards asset purchase - Need to use Asset Register and CRtB scheme more actively - Need to consider bringing the community into process