## Timetable
STAGE | DRAFT TIMETABLE - ESTIMATES 2022/2023 | RESPONSIBLE COMMITTEE | DATE | ACTION
1 | Current Years Forecast Expenditure Compared to Budget and Variations | Finance & General Purposes | 2021-08-11 | Committees note potential ongoing effect of matters reported this year for September budget meetings
|  | Finance & General Purposes | 2021-08-11 | Gauge support in principle for an upper limit % increase in Council Tax (Band D)
|  | Council | 2021-08-16 | Agree in principle an upper limit % increase in Council Tax (Band D)
Set Council priorities for 2022/23
Ask Councillors to Identify New Capital Projects and Funding - particularly if need feasibility funding in 2022/2023
Aim to produce a three year plan for capital and revenue funding
2 | Clerk and Officers to identify budget requirement/priorities for operations | Staffing / Team Meeting | 2/9/2021 - 20/9/2021 | Finance Manager to provide estimate working papers
| Bids for additional funding | All |  | Chairman to consider additional one off funding for councillor led projects
| Identify Savings | All |  | Councillors and Officers to look at options for savings
| Clerk and Finance Manager to Meet Committee Chairs | Planning and Highways Committee | 2021-09-02 | Review existing budget and consider options for 2022/23 - estimate working papers to be provided by Finance Manager
|  | Recreation and Amenities | 2021-09-13 | "
|  | Communications and Policies | 2021-09-15 | "
|  | Finance and General Purposes | 2021-09-15 | "
|  | Staffing Committee | 2021-09-20 | Agree final staffing structure in concultation with staff and consider additional staffing for new facilities , training and pay award - review pension contributions NEST
3 | Committees recommend budget requirement for 2022_23 | Planning and Highways Committee | 2021-09-02 | Agree a detailed estimate, identify additional costs and savings
|  | Recreation and Amenities | 2021-09-30 | "
|  | Communications and Policies | 2021-09-30 | "
|  | Finance and General Purposes | 2021-09-30 | "
|  | Staffing Committee | 2021-10-12 | Finalise Staffing Budget
3 | Consolidate Committee Budgets and Propose Precept | Finance & General Purposes | 2021-11-10 | Consolidate Committee Budgets and Review Impact on Precept
4 | Agree Council Tax and Precept | Council | 2021-12-20 | Finalise Precept
|  |  | 2022-01-17 | Allows for any delay or major changes
5 | Submit Budget requirement /Precept To Borough | Council | 2022-01-31 | Await Letter from WBC
6 | Budget Information/Leaflet | Shinfield Website | 2022-03-01 | Legal requirement to produce a leaflet for precepts over £140,000