CONTRACTOR’S REPORT

Shinfield Community Centre

Project Report

21st June 2021

# CONTENTS

6.1

1.	Progress Report

2.	Health & Safety

3.	Consortium update

4. 	Communications

5.	Catering

6. 	Mobilisation for occupation

Andrew Grimes MSc, MRICS

Project Director

Progress Photographs

- Progress

###### Is measured against the Contract Programme and is for works up to Friday 4th June 2021.

1.1	Contract Details

| Contract commencement | 03/08/20 |
| --- | --- |
| Contract completion date | 02/08/21 |
| Contract period | 52 weeks |
| EOT claimed | 4 week submitted |
| EOT granted | None |
| Current week number | 44 |
| Balance to completion | 8 |
| Target completion | 02/08/21 |
| Anticipated completion | 20/09/21 |

# 1.2	Overview

# Works remain approximately 5 weeks behind programme.

# A claim for an EOT is currently under review.

# A proposed programme to completion is appended to the report which indicates a further 2 weeks delay is anticipated. MEA and AOC are challenging the delays.

# 1.3	Adverse Weather

2 days recorded in period.

14 days total to date

# 1.4	Design Progress

# Budget cost for Bin store forwarded currently awaiting further instruction.

# Internal furniture package drawings issued for review and comment.

# Remedial works to existing parish hall electrical installation has been agreed and instructed.

# Extent of remedial works to existing plumbing installation in existing Parish Hall agreed and currently awaiting confirmation of costs.

# Sonaspray render edge bead approved in lieu of timber batten.

# Cost for reception lobby mural forwarded and awaiting instruction.

# Kitchenette units agreed and instructed.

# Fire shutter specification issued and instructed.

# Guttering to North Elevation of Parish Hall confirmed

# Café beam and column linings under review

# Access panel locations reviewed.

# Fire alarm panel location reviewed.

# Finished ceiling heights reviewed and instructed.

# CCTV camera positions reviewed.

# Soffit cladding reviewed.

# Requirements of proposed café operator under review to be confirmed and instructed.

# Revised finishes schedule issued.

# Anti-slip walkway to flat roof reviewed.

# Internal blinds reviewed.

# Sealant colours agreed.

# Artificial alternative to turf in courtyard proposed awaiting review and instruction

1.5	Site Progress

Community Centre

Aluminium roofing works continue – Outstanding areas to low level of tower awaiting scaffold drop planned for 07.06.21.

External render almost complete – Awaiting scaffold drop.

1st fix M&E almost complete

Internal partitions continue.

Single ply roofing completed to valley gutter.

Parish Hall & Link

Roof finishes almost complete.

Gutters and flashings continue.

1st fix M&E almost continue.

Single ply roofing completed.

Cladding to rear of parapet completed.

1.6	Matters Currently Affecting or Having the Potential to Affect Progress

Extent of strip out of existing mechanical services in the Parish Hall

Resolution of BT wayleave for new service route

Resolution of material queries for café beam and column linings

Resolution of M&E queries to kitchen and kitchen wc.

Resolution of finishes and fit-out to kitchen

1.7	Key activities for the next month

Community Centre

Complete roof finishes and strike external scaffold.

Complete external render to heads & reveals.

Complete 1st fix M&E.

Complete external windows to tower.

Close internal partitions.

Commence 2nd fix M&E.

Commence UFH to screeded areas.

Commence floor screed.

Parish Hall

Complete roof finishes.

Complete floor screed to corridor and link.

Complete 1st fix M&E.

Close partitions and commence plastering.

Commence 2nd fix M&E.

Commence ceilings.

1.8	Materials

# Currently experiencing longer lead time on timber.

# Internal door delivery now expected w/c 12th July 2021 due to production issues.

  - Mains Services

- Electric – New electrical service installed and live, preferred provider for supply confirmed and appointment for meter installation provisionally arranged for the end of June.

- Gas – No new connection required.

- Water – Thames Water connection will be scheduled once service pipe completed to site boundary.

- BT – Details of landowner for access road still awaited from AOC / Client to finalise wayleave and agree route for new service.

- Sewer Connection – Consent to connect received from Thames Water.

# 1.10	Architect / CA Instructions Issued

Nos 1 - 41 received.

- in period

1.11    Instructions recorded on COI

Nos 1-16 issued in period.

1.12    Instructions to be issued:

Upgrade of existing mechanical installation to Parish Hall to remove dead legs etc Revision of M&E installation to kitchen area following survey by proposed café operator.

Termination of services of services in kitchen WC and conversion to store

Detail for Accoya cladding board being reviewed to minimise wastage. Samples for alternative plywood finishes to café beam & columns casings to be reviewed.

Relocation of Fire Alarm panel

Outstanding CVIs

Additional web controller for BMS requested by R&D.

  - Information Required

# Use of diffusion plates to UFH.

# Confirmation 15kw Daikin unit is acceptable.

# Confirmation of leak detection requirements discussed on site with R&D.

Blinds – Confirmation of which option we are to proceed with as email 02/06/21.

Skirting to main hall as email 02/06/21.

Bin store / nursery store and fencing and gating budget costs issued to MEA 19/05/21 – Simplification/Redesign suggested and awaited.

Veneered ply – cost indications and issues with materials issued to MEA 18/05/21 – on going discussion and design and material resolution required.

Option of Astroturf in lieu of turf in rear garden as maintenance is going to be difficult and its quite shaded – decision required.

Mural to ceiling in staircase revised cost issued 25/05/21.

Paint to external columns – either single colour or Two tone as email 28/05/21

Two colour woodwork paint to architraves (to match wall colours) as email 28/05/21.

Approval of porous tarmac specification issued 03/06/21.

1.14     Valuation No 10 has been issued to MEA on 08.06.21 and has been approved by MEA and certified for payment by AOC.

- Health & Safety

0 accidents or incidents to report

1 Safety Inspections in period. Copy of the report is appended.

- Consortium update

Consortium planning application review and confirmed as matching the     Community Centre site levels.

Awaiting way leave for the BT link.

Building Control have approved the temporary escape plan. Awaiting licence for  the strip of land on North East side of the community centre for the escape route.

- Communications

The site hoarding now has 2 banners relating to the project. The newsletter showing the internal layout and room names has been issued.

The naming competition has been started. Responses have been made to the website on the choices. It is planned to make a recommendation by the end of June.

The ongoing delays to construction and BT connectivity are causing delays to fixing the date of the formal opening of the Community Centre.

- Catering

The preferred contractor has been notified and detailed design work has commenced on the kitchen layout. The contractor is now developing a greater understanding of the opportunity and likely offering.

A schedule of heavy kitchen equipment to be purchased by SPC is being developed.

- Mobilisation

The Clerk is developing the mobilisation and occupation programme.