## Sheet1
Shinfield Parish Council Project and Task list |  |  |  | Version 10 11 Mar 2020 | Update | Timescale
No | Project | Lead Councillor / Committee/WP | Current Status | Categorisation by Dev Board 21 2 19
MAJOR PROJECTS
To be performed in sequence not in parallell (a)
1a | New Community Centre Construction | Developent Board Andrew Grimes | Pre-App response received working on final plans and surveys required by WBC | Cannot do 1a and 4a together(resource) so prioritise no1 | Progressing as planned | Q4 2020
2a | External storage at Parish Hall | Developent Board Andrew Grimes | Review additional external storage facility prior to construction of new build. Current external storage area becomes garden | Integrate with 1a | Progressing as planned | Q4 2020
3a | New Community Centre Management | Development Board Andrew Grimes | Work to commence looking at alternative management methods. AG and DP contacted Susan Tyldsley re marketting. Expressions of Interest sent out and 11 iterested, 9 received. AOC meeting 19 09 19 to decide 5 compnies to ask to tender. Meeting arranged for 20 sept to see atrium cafe in Science park. R&A asked to look at mangement options for the running of the SCC. We might employ a buidings manager who will drive the use of the building. | To follow 1a so no work till later on | Progressing as planned | Q4 2020
4a | Replacement of Spencers Wood pavillion | SWP Working Party Ian Clarke Laurie James | SWP WP to take on. Now looks like single story due to roots. Not big enough for library use. M Redfern discussing proposal with property services WBC. | Need 3 quotes. Need to appoint a PM and take this to Full Council as a business case with a Proposal, PM and Principal designer. | Progressing with the plans even if funds not available | 2020-09-01
5a | High Copse Sports Hub | Development Board Ian Clarke Laurie James | Development of sports club and fields |  |  | 2021-09-01
SPC funded with limited involvement/resourse required as will pass to a contractor (b)
1b | Refurbish Spencers Wood Village Hall | Andrew Grimes Village Hall Committee | Waiting response from Spencers Wood Village Hall over Surveyors report and cost of works. No further work done. | Funding only- limited involvement/resource required | No approach fom SWVH so no further action. | 2020
Decision awaited then potential for swift delivery or high involvement ( c )
1c | Development of Deardon Field | R&A Committee Ian Clarke | Waiting response from WBC over exchange of freehold land Deardon/Ryeish Pitches | Awaiting legal decision then swift delivery | Meeting arranged 16th August to progress. Awaiting decision from meeting | Q4 2020
2c | Deardon Field Extension from UoR Freehold Exchange with WBC | I Clarke L James | Waiting receipt of draft 50 year lease from UoR over extended area and management of Allotments | Awaiting legal decision then swift delivery | H O T received and sent to solicitors. The Head Partnership engaged. Lower early | Q4 2020
3c | Village Centre Development | Developent Board Andrew Grimes | Waiting response from Developer consortium and Aldi stores to move to next step. Somon Bream of the consortium contacted AG to say N Sharp will be in touch with a meeting date. Still awaited. No update from Connor on meeting with Consortium. | Aldi is driving this, we can only influence . Once decision is made then high involvement required | Ongoing discussions with Aldi | 2021
5c | Millworth Lane Recreation Ground | R&A Committee Laurie James | Work partially completed waiting for full written proposal for takeover and mangement of site | Legal issues then rapid deployment with little involvement | Lease received and set to solicitors Head partnership | Q4 2019
On hold but could be restarted at any time (d)
Other ( e )
1e | Three Mile Cross Playground and linked to this is: The nacent Green Space at Taylor Wimpey's "South of Church Lane" development - to be made to Parish Council specification instead of Allotments. e.g. Tables and benches etc around flat turfed area, adjacent to the LEPA. | R&A Committee Darrell Lias Nigel Boyer | Possible relocate and re-equip | Allocate to Nigel and Darrell to progress | Progressing with plans developed by WBC | Q4 2019
2e | Mereoak pedestrian crossing | Planning Andrew Grimes | Pedestrian crossing. | WYG prepearing a traffic survey. |  | Q4 2020
PROJECTS
Within committee remit ( f )
1f | Development of pre and after Schools clubs (scoping stage) | CSC WP Ian Montgomery | Operational after School Club at Shinfield term time only review periodically | CSC remit
2f | Chapel Lane Pre-School (scoping stage) | CSC WP Ian Montgomery | Discussion taken place they wish to expand in new building question over term time only to be resolved | CSC remit
Ongoing with Cllr lead (g)
2g | Village Speed Limits | R&A Committeee Darrell Lias | Include Pedestrian access from Shinfiled Meadows as further support for a 20 miles past the school and 30 mile from Shinfield Meadows vehicular access all way through village. | Darrell as lead |  | Q4 2019
3g | Village Gateway signs | R&A Committeee Darrell Lias | Clerk written to WBC re Twyford allowed village gates but not shinfield | Integrate with speeding 2g | Once hear from WBC re village gates can plan. | Q4 2019
TASKS
Within committee remit (h)
2h | Community activity page to be added to SPC website | CSC WP Eddie Brown | In progress. Contributors invited | CSC remit | Specified action has been completed but website review is ongoing separately | Q2 2019
4h | Create maps of SANG walks for all abilities and parents with pushchairs | CSC WP Eddie Brown | In progress with SPVG and WBC. Ian Young aware. Request to add in signs to local amenities ie to shops etc. | CSC remit | Langley Mead is complete. Other SANG walks onging. | Q4 2019
5h | Youth Provision (scoping stage) | CSC WP Ian Montgomery | Investigation by committee looking at needs throughout the parish, working with all groups involved in youth | CSC remit
6h | Pre School Facilities (scoping stage) | CSC WP Eddie Brown | Looking at overall needs for guardian and children and baby facilities and needs versus existing provision for under fives | CSC remit
7h | Disabled Facilities (scoping stage) | CSC WP Peyman Jahromi | Early days project just started | CSC remit
Allocated to Cllrs/Committee (i)
1i | Take over management of WBC land | R&A Committee Ian Clarke Laurie James | New Project waiting for further details of requirements | Longterm project
2i | Pride in our Parish Parish 5 sites | R&A Committee Ian Clarke | Alongside taking over management of WBC land, priority for this work to start soon | Longterm project and merge with 1i above
3i | Development of Parish Brand | Communication & Policies WP Andrew Grimes | Development of improved Parish Brand and better communication with residents | C&P remit
5i | Community Integration Roadshow | CSC WP Eddie Brown | Meeting being arranged with Rev.Paul Willis and Ian Montgomery to plan 2020 roadshow. | CSC remit | Progressing as planned | Q3 2019
6i | Cycle Paths | CSC WP Eddie Brown |  | CSC remit | Progressing as planned
Allocated to Staff (j)
Allocated to Clerk/Office (k)
2k | Property Ownership | Mike Balbini | Clerk to ascertain all SPC property is properly registered with Land Registry | Remit of Clerk / asset management | 16 April 2019 Land registry sent off | Q4 2020
SPC funded with limited involvement/resourse required as will pass to a contractor (l)
1l | Parish Footpaths | Ian Young | On-Going sub contracted to Ray Sharp and Ian Young | SPC allocate funds but work carried put by others. limited involvement required
COMPLETED OR NEARING COMPLETION (m)
1m | Air Polution Equipment | Laurance James | Waiting decision | Completed apart from allocation of schools | 16 April 2019 Locations agreed awaiting installation | Completed
2m | Finalise Parish Hall Upgrade | Mike Balbini | Finalise last items and complete by February Recommend Kitchen Equipment, new china etc | Pass to Clerk and office | 16 April 2019 Completed | Completed
2j | School Green Upgrade | R&A Committee Ian Clarke | Make plan for School Green improvements | Luke to progress with N Boyer | Replaceemnt Oak to be planted in National Tree week in Nov 2019 | Completed
3m | New CCTV for sites | R&A Committee Ian Clarke | Estimates agreed DCS appointed as contractors, insatllers | Awarded to DCSC | 16 April 2019 Completed for office and SWP. Now doing Millworth lane | Completed
4m | S.H.I.N.E (Some Health Issues Need Effort) exercises etc for the over 60's in Shinfield | CSC Committee Eddie Brown | In progress. Agreed with WBC but question of Parish Hall capacity and six mths free use to establish | Approved and bookings made | 16 April 2019 Completed | Completed
2b | Refurbish Grazeley Village Hall | Chair of Council Village Hall Committee | Waiting grant/loan application from Village Hall committee after Surveyors report. Currently finalising and costing required works | Funding only- limited involvement/resource required | Almost complete. Jane has visited to check how grant was spent. | Completed
1j | Patio Upgrade | R&A Committee Ian Clarke | Refurbish Parish Hall patio area | Luke to obtain three quotes | 16 April 2019 Now part of SCC build. Luke to maintain | Completed
1d | Hartley Court Allotments | R&A Committee Ian Clarke | Consider Affodable Homes built by SPC | Place on hold. We can restart at any time
1k | Office management | Mike Balbini | Review on-going specific staff responsibilities, training and development | Remit of Clerk |  | Completed
1h | Newsletter re OAP/Toddler Groups | CSC WP Eddie Brown | In progress. Contributors invited | CSC remit | Completed | Completed
3h | Publicise community activity on SPC Facebook plus Spencer Wood and Shinfield Community Facebooks | CSC WP Eddie Brown | In progress. Contributors invited | CSC remit | Completed | Completed
REMOVED FROM LIST (n)
1n | SOS Save our Villages | SOS Andrew Grimes | On-Going project but at early days needs more integrated marketing approach | Not an SPC project
4i | Change name of parish | Communication & Policies Peter Hughes | Consideration of changing Parish Name to incorporate individual villages in one non controversal name | C&P remit
4c | Empty Bungalows at Ryeish Green | Ian Clark Development Board possible acquisition by SPC and refurb | Look at acquistion of two buildings close to Ryeish for re-furbish and rental by SPC | Awaiting decision then we can start work
Removed
Ongoing
Completed
Merged
Closed / On Hold